## Setup 1
| PCB | Status | CFM |  | Bumper |  | Motor | O-ring |  | Suspension |  | Shell
|  |  | Material | version | Material | version |  | Material | version | Material | version | Material | version | color | comments
| IC69200A44F8 | assembled | TPU95A %80 infill | V1 35 mm | TPU95A 15% infill | V1 | TS90M1 | NBR 90 | 25 mm | x | x | x | x | x | x
Eventlog | Date | Event
| 2025-12-29 | Testing for 30 min full speed
No effect seen
| 2026-01-21 | Assembled in Yellow ball (baseball design) | [7 empty] | TPU95A polymaker 15% infill | V1 | TPU95A polymaker 15% infill | V1 | Yellow | Baseball design with two screws for easy acces
| 2026-01-21 | Tested at BSO location. Children kicked the ball hard -> no imidiate damage reported - connection los when kicked hard - cause unknown
| 2026-02-11 | Highlight Delft (4 days)
| 2026-02-11 | battery was drained to 40% after 5 hours of use after day one
| 2026-02-12 | battery was drained to ~40% after 5 hours of use after day one
| 2026-04-02 | motor-axis connection got loose. Locktide or instant glue was not working properly.
| 2026-04-09 | took apart the drivetrain. Only one 4mm and 3mm bearing left and no fixed axis
| may + june | Used By the BEP group to test and read out IMU data
In the end not used by the BEP group

## Setup 2
| PCB | Status | CFM |  | Bumper |  | Motor | O-ring |  | Suspension |  | Shell
|  |  | Material | version | Material | version |  | Material | version | Material | version | Material | version | comments
| IC69200A4F78 | assembled | x | x | x | x | x | x | x | x | x | x | x | x
Eventlog | Date | Event
| 2026-02-10 | assembled for highlight delft | TPC 40D green | V1 35 mm | TPC 40D green | V1 | TS90M2 | NBR 90 | 24 mm | TPC 40D green | with inside connection | TPC 40D green | Soccerball | Printed in two parts
| 2026-02-11 | Highlight Delft (4 days)
battery was drained to ~40% after 5 hours of use after day one
| 2026-02-12 | 30% battery left. Did see a bit more connection lost, could not figure out why.
| months may through june | Used by BEP group for classification
| 2026-05-02 | Added a washer to the battery, for better clamping force
| 2026-05-29 | Added a small wooden stick to the battery holder to clamp down the battery. This worked well.
| 2026-05-29 | The motor pulley connection with the screw broke off. Fixed it by using the two holes in the pulley to connect to the motor connector and then to the motor

## Setup 3
| PCB | Status | CFM |  | Bumper |  | Motor | O-ring |  | Suspension |  | Shell
|  |  | Material | version | Material | version |  | Material | version | Material | version | Material | version | color | comments
NEW from aachen | 1C69200A4F58 | assembled | x | x | x | x | x | x | x | x | x | x | x | x | x
Eventlog | Date | Event
| 2026-02-06 | Arrived from Aachen to use as backup
| 2026-02-12 | assembled with CFM and battery | TPC 40D red | V1 35 mm | TPC 40D red | V1 | TS90M3 | NBR 90 | 24 mm | TPU95A Black | old one through the shell | TPU95A Black | old | Black | Used as demo
used as backup for highlight delft
| 2026-04-09 | rebuild new version for soccerball design | [6 empty] | 23 mm | polymaker TPU 90A | with inside connection | polymaker TPU 90A | Soccerball | Teal | printed in 2 parts
| 2026-05-11 | Lend version to bachelor student Twente, added a washer, changed the o-ring | [6 empty] | 22 mm?
| 2026-05-27 | screw to the motor got loose (the one that is inside the pulley, after re assembling it worked again
| 2026-06-17 | Size of the o-ring is now 23mm, don't know if it has been stretched to this length or that it stayed that way
| 2026-06-17 | Took the drivetrain apart to test with new CFMs: the pulley is now very close to the pcb, setscrew has to be tightend before turning the pulley

## Setup 4
| PCB | Status | CFM |  | Bumper |  | Motor | O-ring |  | Suspension |  | Shell
|  |  | Material | version | Material | version |  | Material | version | Material | version | Material | version | color | comments
| IC69200A4F64 | assembled | TPU95A %80 infill | V1 35 mm | TPU95A 15% infill | V1 | TS90M4 | NBR 90 | 25 mm | TPU95A %80 infill | V1 | TPU95A 15% infill | V1 | Black | One wall on the inside
Eventlog | Date | Event
| 2025-09-01 | Given to Product now studio course
| 2026-02-12 | Returned from Product now studio course Broken motor connector on the pcb Students fixed it by adding wires and soldering them to the PCB at other points Taken out of the black shell and used the bearings for setup 3
| 2026-04-02 | replaced the drivetrain in the yellow ball. Also took the bumper from the setup 1 and the extra brass weights. | [7 empty] | TPU95A polymaker 15% infill | V1 | TPU95A polymaker 15% infill | V1 | Yellow | Baseball design with two screws for easy acces